## Submittal Log (050919)
|  | Submitted |  | PROJECT | COBBS CREEK PLAYGROUND
|  | Reviewed |  | ADDRESS | 700 Cobbs Creek Parkway
|  | Late |  | PHDC PM | TBD
|  | Returned |  | REBUILD (RB) PM | SARA NORDSTROM
|  | Resubmit |  | GC | TBD
|  | Not used |  | AE | NICK JABS, PORT
|  |  |  | INSPECTOR | TBD
| AE/RB/PHDC |  |  |  |  | GC | GC | AE/RB/PHDC | AE/RB/PHDC | GC | AE/RB/PHDC | AE/RB/PHDC | AE/RB/PHDC
Section | Status (Color Code) | From Company | Sub. Code | Submittal Description | Copy To | Planned Start of Trade Work | Planned Submittal Date | Actual Submittal Date | Submittal Return Date (+10) | Planned Resubmittal Date | Actual Resubmittal Date | Resubmittal Return Date (+10) | Action | Reviewed By
PRE-CONSTRUCTION SUBMITTALS - PRIOR TO NTP
|  | PHDC |  | Notice of Contract Award | Rebuild | [8 empty] | Rebuild/PHDC
|  | PHDC |  | Executed Contract | Rebuild | [8 empty] | Rebuild/PHDC
007200 |  | GC |  | Certificate of Payment Bond | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
002113 |  | GC |  | Certificate of Performance Bond | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
007200 |  | GC |  | Certificate of Insurance (including Workers Comp) | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
|  | GC |  | REBUILD: Project Economic Opportunity Commitment Form | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
|  | GC |  | REBUILD: Contract Participation Form Worksheet | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
|  | GC |  | REBUILD: Project Worforce Diversity Worksheet | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
|  | GC |  | COVID-19 Safety Plan per City of Philadelphia Requirements | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
007200 |  | GC |  | Company Safety Program | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
007200 |  | GC |  | Site Specific Safety Plan | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
012973 |  | GC |  | Schedule of Values | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
012200 |  | GC |  | Unit Prices | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
013113 |  | GC |  | List of Contractors' staff assignments | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
013113 |  | GC |  | List of Contractor's Principal Consultants | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
013113 |  | GC |  | List of subcontractors | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
013113 |  | GC |  | List of principal suppliers and fabricators | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
013216 |  | GC |  | Initial Construction Schedule | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
013513.18 |  | GC |  | Phasing and Logistics Plan | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
013513.18 |  | GC |  | PPR Permits (GC and all subs) | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
CONSTRUCTION SUBMITTALS - POST NTP
|  | PHDC |  | Notice to Proceed (NTP) | Rebuild | [8 empty] | Rebuild/PHDC
002114 |  | GC |  | Diesel Engine Emissions Controls Compliance - per covered vehicle | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
013216 |  | GC |  | Final Construction Schedule | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
013216 |  | GC |  | Submittal Schedule (this document) | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
013226 |  | GC |  | Monthly Reports 01 | Rebuild/PHDC | [8 empty] | Rebuild/PHDC/AE
013226 |  | GC |  | Monthly Reports 02 | Rebuild/PHDC | [8 empty] | Rebuild/PHDC/AE
013226 |  | GC |  | Monthly Reports 03 | Rebuild/PHDC | [8 empty] | Rebuild/PHDC/AE
013226 |  | GC |  | Monthly Reports 04 | Rebuild/PHDC | [8 empty] | Rebuild/PHDC/AE
013226 |  | GC |  | Monthly Reports 05 | Rebuild/PHDC | [8 empty] | Rebuild/PHDC/AE
013226 |  | GC |  | Monthly Reports 06 | Rebuild/PHDC | [8 empty] | Rebuild/PHDC/AE
013233 |  | GC |  | Initial pre-construction photographs | Rebuild/PHDC/AE | [8 empty] | Rebuild/PHDC
015000 |  | GC |  | Temporary Facilities Submittals | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
|  | GC |  | Onsite Labor Osha 10 Cards | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
|  | GC |  | OSHA 300 Form Posted | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
015639 |  | GC |  | Temporary Tree and Plant Protection - Shop Drawings | Rebuild/PHDC/AE | [8 empty] | AE
015639 |  | GC |  | Temporary Tree and Plant Protection - Mulch Sample | Rebuild/PHDC/AE | [8 empty] | AE
015639 |  | GC |  | Temporary Tree and Plant Protection - Arborist Report | Rebuild/PHDC/AE | [8 empty] | AE
015639 |  | GC |  | Temporary Tree and Plant Protection - Arborist Qualification Data | Rebuild/PHDC/AE | [8 empty] | AE
015639 |  | GC |  | Temporary Tree and Plant Protection - Arborist Certification | Rebuild/PHDC/AE | [8 empty] | AE
015639 |  | GC |  | Temporary Tree and Plant Protection - Existing Conditions Documentation | Rebuild/PHDC/AE | [8 empty] | AE
015639 |  | GC |  | Temporary Tree and Plant Protection - Quality-Control Program | Rebuild/PHDC/AE | [8 empty] | AE
015800 |  | GC |  | Project Identification and Signs - Shop Drawing | Rebuild/PHDC
017123 |  | GC |  | Field Engineering - Surveyor Info | Rebuild/PHDC/AE | [8 empty] | AE
017123 |  | GC |  | Field Engineering - Verification of Accuracy | Rebuild/PHDC/AE | [8 empty] | AE
017123 |  | GC |  | Field Engineering - Reference Point Survey | Rebuild/PHDC/AE | [8 empty] | AE
017123 |  | GC |  | Field Engineering - Surveyor Certification | Rebuild/PHDC/AE | [8 empty] | AE
017419 |  | GC |  | Waste Management Plan | Rebuild/PHDC/AE | [8 empty] | AE
017419 |  | GC |  | Waste Reduction Progress Reports | Rebuild/PHDC/AE | [8 empty] | AE
017419 |  | GC |  | Waste Reduction Calculations | Rebuild/PHDC/AE | [8 empty] | AE
017419 |  | GC |  | Records of Donations | Rebuild/PHDC/AE | [8 empty] | AE
017419 |  | GC |  | Records of Sales | Rebuild/PHDC/AE | [8 empty] | AE
017419 |  | GC |  | Recycling and Processing Facility Records | Rebuild/PHDC/AE | [8 empty] | AE
017419 |  | GC |  | Landfill and Incinerator Disposal Records | Rebuild/PHDC/AE | [8 empty] | AE
017419 |  | GC |  | LEED Submittals | Rebuild/PHDC/AE | [8 empty] | AE
017419 |  | GC |  | Qualification Data | Rebuild/PHDC/AE | [8 empty] | AE
017419 |  | GC |  | Statement of Refrigerant Recovery | Rebuild/PHDC/AE | [8 empty] | AE
017700 |  | GC |  | Notice of Substantial Completion | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
017700 |  | PHDC |  | Certificate of Substantial Completion | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
017700 |  | GC |  | Certificate of Occupancy | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
017700 |  | GC |  | Certificates of Inspection by Governing Authority | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
017700 |  | GC |  | Keys & Keying Schedule | Rebuild/PHDC/AE | [8 empty] | AE
017700 |  | GC |  | Evidence of Payment and Release of Liens | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
017700 |  | GC |  | Consent of Surety | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
017700 |  | GC |  | Final Statement of Accounting | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
017839 |  | GC |  | Project Record Documents | Rebuild/PHDC/AE | [8 empty] | Rebuild/PHDC/AE
017700 |  | GC |  | Notice of Final Completion | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
017700 |  | PHDC/GC |  | Project Closeout Audit | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
017700 |  | PHDC |  | Project Closeout Form | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
PROJECT MATERIALS SUBMITTALS
022310 |  | GC | PD | Tree Protection, Trimming and Relocation - Product Data | Rebuild/PHDC/AE | [8 empty] | AE
022310 |  | GC | QD | Tree Protection, Trimming and Relocation - "Quality assurance" firm | Rebuild/PHDC/AE | [8 empty] | AE
022310 |  | GC | CERT | Tree Protection, Trimming and Relocation - Arborist Certification | Rebuild/PHDC/AE | [8 empty] | AE
022310 |  | GC | MD | Tree Protection, Trimming and Relocation - Arborist Maintenance Recommendatios | Rebuild/PHDC/AE | [8 empty] | AE
022310 |  | GC | OTHER | Tree Protection, Trimming and Relocation - list of eqpt, procedure, labor force | Rebuild/PHDC/AE | [8 empty] | AE
022310 |  | GC | OTHER | Tree Protection, Trimming and Relocation - schedule for tree digging and relocation | Rebuild/PHDC/AE | [8 empty] | AE
024119 |  | GC | OTHER | Selective Demolition: Proposed protection measures Report/drawings | Rebuild/PHDC/AE | [8 empty] | AE
024119 |  | GC | OTHER | Selective Demolition: Schedule of selective demolition activities | Rebuild/PHDC/AE | [8 empty] | AE
024119 |  | GC | OTHER | Selective Demolition: Predemolition photographs or video | Rebuild/PHDC/AE | [8 empty] | AE
024119 |  | GC | OTHER | Selective Demolition: Inventory of items removed and salvaged | Rebuild/PHDC/AE | [8 empty] | AE
033000 |  | GC | PD | Cast-in-place Concrete: Product Data | Rebuild/PHDC/AE | [8 empty] | AE
033000 |  | GC | PD | Cast-in-place Concrete: Concrete Design Mixture | Rebuild/PHDC/AE | [8 empty] | AE
033000 |  | GC | SD | Cast-in-place Concrete: Construction Joint Layout - Shop Drawings | Rebuild/PHDC/AE | [8 empty] | AE
033000 |  | GC | QD | Cast-in-place Concrete: Installer Qualifications | Rebuild/PHDC/AE | [8 empty] | AE
033000 |  | GC | CERT | Cast-in-place Concrete: Material Certificates | Rebuild/PHDC/AE | [8 empty] | AE
033000 |  | GC | OTHER | Cast-in-place Concrete: Material Test Reports | Rebuild/PHDC/AE | [8 empty] | AE
033000 |  | GC | QCR | Cast-in-place Concrete: Field quality-control reports | Rebuild/PHDC/AE | [8 empty] | AE
100610 |  | GC | SD | Exterior Signage - Shop Drawings | Rebuild/PHDC/AE | [8 empty] | AE
100610 |  | GC | SAM | Exterior Signage - Color Samples | Rebuild/PHDC/AE | [8 empty] | AE
100610 |  | GC | SAM | Exterior Signage - Materials Samples | Rebuild/PHDC/AE | [8 empty] | AE
100610 |  | GC | SD | Exterior Signage - CHPL Samples - PDF Proof | Rebuild/PHDC/AE | [8 empty] | AE
116800 |  | GC | PD | Play Equipment - Product Data | Rebuild/PHDC/AE | [8 empty] | AE
116800 |  | GC | PD | Play Equipment - Equipment Materials/Color Selection | Rebuild/PHDC/AE | [8 empty] | AE
116800 |  | GC | SD | Play Equipment - Coordination Drawings | Rebuild/PHDC/AE | [8 empty] | AE
116800 |  | GC | QD | Play Equipment - Installer and Testing Agency Qualitifactions | Rebuild/PHDC/AE | [8 empty] | AE
116800 |  | GC | CERT | Play Equipment - Product certificate for each piece of equipment | Rebuild/PHDC/AE | [8 empty] | AE
116800 |  | GC | SW | Play Equipment - Manufacturer's special warranties | Rebuild/PHDC/AE | [8 empty] | AE
116800 |  | GC | MD | Play Equipment - Maintenance manual | Rebuild/PHDC/AE | [8 empty] | AE
116800.01 |  | GC | PD | Sprayground System - Product Data | Rebuild/PHDC/AE | [8 empty] | AE
116800.01 |  | GC | SD | Sprayground System - System layout drawings | Rebuild/PHDC/AE | [8 empty] | AE
116800.01 |  | GC | SD | Sprayground System - Record Drawings of installed system | Rebuild/PHDC/AE | [8 empty] | AE
116800.01 |  | GC | PD | Sprayground System - Materials/Color Selection | Rebuild/PHDC/AE | [8 empty] | AE
116800.01 |  | GC | MD | Sprayground System - Sprayground Operation and Maintenance Manual | Rebuild/PHDC/AE | [8 empty] | AE
116800.01 |  | GC | QD | Sprayground System - Installer Qualifitications | Rebuild/PHDC/AE | [8 empty] | AE
129300 |  | GC | PD | Site Furnishings - Benches Product Data | Rebuild/PHDC/AE | [8 empty] | AE
129300 |  | GC | PD | Site Furnishings - Trash and Recycling Receptacles Product Data | Rebuild/PHDC/AE | [8 empty] | AE
129300 |  | GC | PD | Site Furnishings - Drinking Fountain and Bottle Filling Station Product Data | Rebuild/PHDC/AE | [8 empty] | AE
129300 |  | GC | MD | Site Furnishings - Site furnishing maintenance manual | Rebuild/PHDC/AE | [8 empty] | AE
260519 |  | GC | PD | Low-voltage electrical power conductors and cables - Product Data | Rebuild/PHDC/AE | [8 empty] | AE
260519 |  | GC | OTHER | Low-voltage electrical power conductors and cables - Product schedule | Rebuild/PHDC/AE | [8 empty] | AE
260526 |  | GC | PD | Grounding and bonding for electrical systems - Product Data | Rebuild/PHDC/AE | [8 empty] | AE
260526 |  | GC | MD | Grounding and bonding for electrical systems - Operation and Maintenance Data | Rebuild/PHDC/AE | [8 empty] | AE
260526 |  | GC | SD | Grounding and bonding for electrical systems - As-built drawings of system | Rebuild/PHDC/AE | [8 empty] | AE
260533 |  | GC | PD | Raceways and boxes for electrical systems - Product Data | Rebuild/PHDC/AE | [8 empty] | AE
260533 |  | GC | SD | Raceways and boxes for electrical systems - Shop Drawings | Rebuild/PHDC/AE | [8 empty] | AE
260543 |  | GC | PD | Underground Ducts and Raceways for Electrical Systems - Product Data | Rebuild/PHDC/AE | [8 empty] | AE
260543 |  | GC | SD | Underground Ducts and Raceways for Electrical Systems - Shop Drawings | Rebuild/PHDC/AE | [8 empty] | AE
260543 |  | GC | SD | Underground Ducts and Raceways for Electrical Systems - Coordination Drawings | Rebuild/PHDC/AE | [8 empty] | AE
260553 |  | GC | PD | Identification for Electrical Systems - Product Data | Rebuild/PHDC/AE | [8 empty] | AE
260553 |  | GC | OTHER | Identification for Electrical Systems - Delegated-Design Submittal | Rebuild/PHDC/AE | [8 empty] | AE
260923 |  | GC | PD | Lighting Control Devices - Product Data | Rebuild/PHDC/AE | [8 empty] | AE
260923 |  | GC | QCR | Lighting Control Devices - field quality-control reports | Rebuild/PHDC/AE | [8 empty] | AE
262416 |  | GC | PD | Panelboards - Product Data | Rebuild/PHDC/AE | [8 empty] | AE
262416 |  | GC | PD | Panelboards - Shop Drawings | Rebuild/PHDC/AE | [8 empty] | AE
262416 |  | GC | QD | Panelboards - Qualification data for testing agency | Rebuild/PHDC/AE | [8 empty] | AE
262416 |  | GC | OTHER | Panelboards - Panelboard schedules | Rebuild/PHDC/AE | [8 empty] | AE
262416 |  | GC | MD | Panelboards - Operation and Maintenance Data | Rebuild/PHDC/AE | [8 empty] | AE
262416 |  | GC | OTHER | Panelboards - Keys - two spares for each type of panelboard cabinet lock. | Rebuild/PHDC/AE | [8 empty] | AE
262726 |  | GC | PD | Wiring Devices - Product Data | Rebuild/PHDC/AE | [8 empty] | AE
262726 |  | GC | SD | Wiring Devices - Shop Drawings | Rebuild/PHDC/AE | [8 empty] | AE
262726 |  | GC | SAM | Wiring Devices - Samples | Rebuild/PHDC/AE | [8 empty] | AE
262816 |  | GC | PD | Enclosed Switches and Circuit Breakers - Product Data | Rebuild/PHDC/AE | [8 empty] | AE
262816 |  | GC | SD | Enclosed Switches and Circuit Breakers - Shop Drawings | Rebuild/PHDC/AE | [8 empty] | AE
262816 |  | GC | SW | Enclosed Switches and Circuit Breakers - Manufactuer's Warranty | Rebuild/PHDC/AE | [8 empty] | AE
311000 |  | GC | OTHER | Site Clearing - Existing conditions documentation | Rebuild/PHDC/AE | [8 empty] | AE
311000 |  | GC | SD | Site Clearing - Record Drawings | Rebuild/PHDC/AE | [8 empty] | AE
312000 |  | GC | PD | Earth Moving - Product Data | Rebuild/PHDC/AE | [8 empty] | AE
312500 |  | GC | PD | Soil Erosion and Sediment Control - Product Data | Rebuild/PHDC/AE | [8 empty] | AE
321216 |  | GC | PD | Asphalt Paving - Product Data | Rebuild/PHDC/AE | [8 empty] | AE
321216 |  | GC | PD | Asphalt Paving - Hot-mix Ashpalt Designs | Rebuild/PHDC/AE | [8 empty] | AE
321216 |  | GC | OTHER | Asphalt Paving - Material Test Report | Rebuild/PHDC/AE | [8 empty] | AE
321216 |  | GC | CERT | Asphalt Paving - Material Certificates | Rebuild/PHDC/AE | [8 empty] | AE
321313 |  | GC | PD | Concrete Paving - Product Data | Rebuild/PHDC/AE | [8 empty] | AE
321313 |  | GC | PD | Concrete Paving - Design Mixtures | Rebuild/PHDC/AE | [8 empty] | AE
321723 |  | GC | PD | Pavement Markings - Product Data | Rebuild/PHDC/AE | [8 empty] | AE
321723 |  | GC | SAM | Pavement Markings - Samples for each color | Rebuild/PHDC/AE | [8 empty] | AE
321816.13 |  | GC | PD | Playground Protective Surfacing - Product Data | Rebuild/PHDC/AE | [8 empty] | AE
321816.13 |  | GC | SD | Playground Protective Surfacing - Shop Drawings | Rebuild/PHDC/AE | [8 empty] | AE
321816.13 |  | GC | SD | Playground Protective Surfacing - Coordination Drawings | Rebuild/PHDC/AE | [8 empty] | AE
321816.13 |  | GC | SAM | Playground Protective Surfacing - Samples for each exposed finish (initial) | Rebuild/PHDC/AE | [8 empty] | AE
321816.13 |  | GC | SAM | Playground Protective Surfacing - Samples for each exposed finish (Verification) | Rebuild/PHDC/AE | [8 empty] | AE
321816.13 |  | GC | QD | Playground Protective Surfacing - Qualification Data and Certification for installer | Rebuild/PHDC/AE | [8 empty] | AE
321816.13 |  | GC | OTHER | Playground Protective Surfacing - Product Test Reports | Rebuild/PHDC/AE | [8 empty] | AE
321816.13 |  | GC | QCR | Playground Protective Surfacing - Field quality-control reports | Rebuild/PHDC/AE | [8 empty] | AE
321816.13 |  | GC | SW | Playground Protective Surfacing - Sample of special warranty | Rebuild/PHDC/AE | [8 empty] | AE
321816.33 |  | GC | PD | Cork Playground Protective Surfacing - Product Data | Rebuild/PHDC/AE | [8 empty] | AE
321816.33 |  | GC | SAM | Cork Playground Protective Surfacing - Verification Samples | Rebuild/PHDC/AE | [8 empty] | AE
321816.33 |  | GC | QD | Cork Playground Protective Surfacing - Qualification Data for installer | Rebuild/PHDC/AE | [8 empty] | AE
321816.33 |  | GC | SW | Cork Playground Protective Surfacing - Warranty Documents | Rebuild/PHDC/AE | [8 empty] | AE
329113 |  | GC | PD | Soil Preperation - Product Data | Rebuild/PHDC/AE | [8 empty] | AE
329113 |  | GC | SAM | Soil Preperation - Material samples | Rebuild/PHDC/AE | [8 empty] | AE
329113 |  | GC | SAM | Soil Preperation - Mixes samples | Rebuild/PHDC/AE | [8 empty] | AE
329113 |  | GC | OTHER | Soil Preperation - name of off-site, proposed base toposil | Rebuild/PHDC/AE | [8 empty] | AE
329113 |  | GC | QD | Soil Preperation - Qualification data for testing agency, soil mix manufacturer | Rebuild/PHDC/AE | [8 empty] | AE
329113 |  | GC | OTHER | Soil Preperation - Test Reports | Rebuild/PHDC/AE | [8 empty] | AE
329113 |  | GC | QCR | Soil Preperation - Field Quality-Control Reports | Rebuild/PHDC/AE | [8 empty] | AE
329200 |  | GC | QD | Turf and Grasses - Qualification data for landscape installer | Rebuild/PHDC/AE | [8 empty] | AE
329200 |  | GC | CERT | Turf and Grasses - Certification of grass seed | Rebuild/PHDC/AE | [8 empty] | AE
329200 |  | GC | CERT | Turf and Grasses - Product Certificates | Rebuild/PHDC/AE | [8 empty] | AE
329200 |  | GC | OTHER | Turf and Grasses - Pesticides and Herbicides specific instructions | Rebuild/PHDC/AE | [8 empty] | AE
329200 |  | GC | MD | Turf and Grasses - Maintenance Data | Rebuild/PHDC/AE | [8 empty] | AE
329300 |  | GC | PD | Plants - Product Data | Rebuild/PHDC/AE | [8 empty] | AE
329300 |  | GC | QD | Plants - Qualification data for landscape installer | Rebuild/PHDC/AE | [8 empty] | AE
329300 |  | GC | CERT | Plants - Product Certificates | Rebuild/PHDC/AE | [8 empty] | AE
329300 |  | GC | OTHER | Plants - Pesticides and Herbicides specific instructions | Rebuild/PHDC/AE | [8 empty] | AE
329300 |  | GC | OTHER | Plants - Notices and Scheduling | Rebuild/PHDC/AE | [8 empty] | AE
329300 |  | GC | OTHER | Plants - Plant list and source identification | Rebuild/PHDC/AE | [8 empty] | AE
329300 |  | GC | OTHER | Plants - Documentation of unavailability of plant material | Rebuild/PHDC/AE | [8 empty] | AE
329300 |  | GC | CERT | Plants - Certificates | Rebuild/PHDC/AE | [8 empty] | AE
329300 |  | GC | OTHER | Plants - Project status prior to installation ('J') | Rebuild/PHDC/AE | [8 empty] | AE
329300 |  | GC | SW | Plants - Special warranty | Rebuild/PHDC/AE | [8 empty] | AE
329300 |  | GC | MD | Plants - Maintenance Instructions | Rebuild/PHDC/AE | [8 empty] | AE
329600 |  | GC | PD | Transplanting - Product Data | Rebuild/PHDC/AE | [8 empty] | AE
329600 |  | GC | OTHER | Transplanting - Pruning Schedule | Rebuild/PHDC/AE | [8 empty] | AE
329600 |  | GC | QD | Transplanting - Qualification data for tree-service and arborist | Rebuild/PHDC/AE | [8 empty] | AE
329600 |  | GC | CERT | Transplanting - from arborist re: tree status during construction | Rebuild/PHDC/AE | [8 empty] | AE
329600 |  | GC | MD | Transplanting - Maintenance Recommendations | Rebuild/PHDC/AE | [8 empty] | AE
329600 |  | GC | OTHER | Transplanting - Documenation of existing trees to be transplatning | Rebuild/PHDC/AE | [8 empty] | AE
331417 |  | GC | PD | Site Water Service Utility Laterals - Product Data | Rebuild/PHDC/AE | [8 empty] | AE
331417 |  | GC | CERT | Site Water Service Utility Laterals - Manufactuer's Certificate and Instructions | Rebuild/PHDC/AE | [8 empty] | AE
331417 |  | GC | QCR | Site Water Service Utility Laterals - Field Quality-control submittals | Rebuild/PHDC/AE | [8 empty] | AE
331417 |  | GC | QD | Site Water Service Utility Laterals - Qualifications Statement | Rebuild/PHDC/AE | [8 empty] | AE
331417 |  | GC | SD | Site Water Service Utility Laterals - Project Record Documents | Rebuild/PHDC/AE | [8 empty] | AE
CONSTRUCTION PERMIT LOG (insert rows as required)
007200 |  | GC |  |  | Rebuild/PHDC/AE | [8 empty] | Rebuild/PHDC/AE
007200 |  | GC |  |  | Rebuild/PHDC/AE | [8 empty] | Rebuild/PHDC/AE
SPECIAL INSPECTION LOG (insert rows as required)
014516.13 |  | GC |  | Brief description of inspection. | Rebuild/PHDC/AE | [8 empty] | Rebuild/PHDC/AE
014516.13 |  | GC |  | Brief description of inspection. | Rebuild/PHDC/AE | [8 empty] | Rebuild/PHDC/AE
014516.13 |  | GC |  | Brief description of inspection. | Rebuild/PHDC/AE | [8 empty] | Rebuild/PHDC/AE
REQUEST FOR INFORMATION ("RFIs") LOG (insert rows as required)
|  | GC |  | Number and brief description of RFI. | Rebuild/PHDC/AE | [8 empty] | AE
|  | GC |  | Number and brief description of RFI. | Rebuild/PHDC/AE | [8 empty] | AE
|  | GC |  | Number and brief description of RFI. | Rebuild/PHDC/AE | [8 empty] | AE
|  | GC |  | Number and brief description of RFI. | Rebuild/PHDC/AE | [8 empty] | AE
SUBSTITUTION REQUEST LOG (insert rows as required)
012500 |  | GC |  | Number and brief description of substitution. | Rebuild/PHDC/AE | [8 empty] | AE
012500 |  | GC |  | Number and brief description of substitution. | Rebuild/PHDC/AE | [8 empty] | AE
012500 |  | GC |  | Number and brief description of substitution. | Rebuild/PHDC/AE | [8 empty] | AE
CHANGE ORDER REQUEST LOG (insert rows as required)
012600 |  | GC |  | Number and brief description of change order. | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
012600 |  | GC |  | Number and brief description of change order. | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
012600 |  | GC |  | Number and brief description of change order. | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
PAYMENT REQUEST LOG (insert rows as required)
012900 |  | GC |  | Initial | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
012900 |  | GC |  | Monthly | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
012900 |  | GC |  | Monthly | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
012900 |  | GC |  | Monthly | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
012900 |  | GC |  | Substantial Completion | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
012900 |  | GC |  | Final | Rebuild/PHDC | [8 empty] | Rebuild/PHDC
|  | Submitted |  |  | CERT | Certificate
|  | Reviewed |  |  | FS | Field Sample
|  | Late |  |  | MD | Maintenance Data
|  | Returned |  |  | MU | Mockup
|  | Resubmit |  |  | OTHER | Other
|  | Not used |  |  | PD | Product Data
[5 empty] | QCR | Quality Control Report
[5 empty] | QD | Qualification Data
[5 empty] | SAM | Sample
[5 empty] | SD | Shop Drawing
[5 empty] | SP | Spare Parts/Maintenance Materials
[5 empty] | SW | Sample Warranty
[5 empty] | TR | Training