## Sheet1
|  |  | Submitted |  | SD | Shop Drawing
|  |  | Reviewed |  | S | Sample
Late
Returned
Resubmit
Not used
Number | Section | Page | From Company | Submittal Description | Copy To | Planned Start of Trade Work | Planned Submittal Date | Actual Submittal Date | Submittal Return Date +14 | Planned Resubmittal Date | Actual Resubmittal Date | Resubmittal Return Date +14 | Action | Reviewed By
1 | Division 1 |  | PRA | Narrative- Monthly (for all projects over 4 weeks) | Rebuild/PRA/AE | Enter | Monthly | [6 empty] | Rebuild/AE/PPR
2 |  |  | PRA | Certificate of Insurance (including Workers Comp) | Rebuild/PRA/AE | Estimated | Pre Construction | [6 empty] | Rebuild/AE/PPR
3 |  |  | PRA | Certificate of Payment and Performance Bond | Rebuild/PRA/AE | Dates | Pre Construction | [6 empty] | Rebuild/AE/PPR
4 |  |  | PRA | Bid Award | Rebuild/PRA/AE | This | Pre Construction | [6 empty] | Rebuild/AE/PPR
5 |  |  | PRA | Executed Contract | Rebuild/PRA/AE | Column | Pre Construction | [6 empty] | Rebuild/AE/PPR
6 |  |  | GC | Project Baseline Schedule | Rebuild/PRA/AE | ….. | Pre Construction | [6 empty] | Rebuild/AE/PPR
7 |  |  | GC | Schedule of Values | Rebuild/PRA/AE | … | Pre Construction | [6 empty] | Rebuild/AE/PPR
8 |  |  | GC | LCP Tracker (confirmation of use Prime & Subs) | Rebuild/PRA/AE | … | Pre Construction | [6 empty] | Rebuild/AE/PPR
9 |  |  | GC | Project Estimated Hours | Rebuild/PRA/AE |  | Pre Construction | [6 empty] | Rebuild/AE/PPR
10 |  |  | GC | Project Estimated WMBE Targets Summary Sheet | Rebuild/PRA/AE |  | Pre Construction | [6 empty] | Rebuild/AE/PPR
11 |  |  | GC | Project Worforce Diversity Plan | Rebuild/PRA/AE |  | Pre Construction | [6 empty] | Rebuild/AE/PPR
12 |  |  | PRA/GC | Project Contact List (including subcontractors) | Rebuild/PRA/AE |  | Pre Construction | [6 empty] | Rebuild/AE/PPR
13 |  |  | PRA | Pre-Construction Meeting Minutes | Rebuild/PRA/AE |  | For Record | [6 empty] | Rebuild/AE/PPR
13 |  |  | GC | Onsite Labor Osha 10 Cards | Rebuild/PRA/AE |  | Pre Construction | [6 empty] | Rebuild/AE/PPR
14 |  |  | GC | OSHA 300 Form Posted | Rebuild/PRA/AE |  | Pre Construction | [6 empty] | Rebuild/AE/PPR
15 |  |  | GC | Company Safety Program | Rebuild/PRA/AE |  | Pre Construction | [6 empty] | Rebuild/AE/PPR
16 |  |  | GC | Site Specific Safety Plan | Rebuild/PRA/AE |  | Pre Construction | [6 empty] | Rebuild/AE/PPR
17 |  |  | GC | Phasing and Logistics Plan | Rebuild/PRA/AE |  | Pre Construction | [6 empty] | Rebuild/AE/PPR
18 |  |  | PRA/GC | Project Specific Submittal log (PD, Shop Drawings, Samples) | Rebuild/PRA/AE |  | Pre Construction | [6 empty] | Rebuild/AE/PPR
19 |  |  | GC | Submittal Cover Sheet Form | Rebuild/PRA/AE |  | Pre Construction | [6 empty] | Rebuild/AE/PPR
20 |  |  | PRA | Project Labor Agreement (contracts above 3 million) | Rebuild/PRA/AE | n/a | As Required | [6 empty] | Rebuild/AE/PPR
21 |  |  | PRA | Workforce MOU | Rebuild/PRA/AE | n/a | As Required | [6 empty] | Rebuild/AE/PPR
22 |  |  | PRA/GC | Maintain Permits Log- (L&I, PWD, etc) | Rebuild/PRA/AE |  | Pre Construction | [6 empty] | Rebuild/AE/PPR
23 |  |  | CITY | Street Department Approval | Rebuild/PRA/AE |  | As Required | [6 empty] | Rebuild/AE/PPR
24 |  |  | CITY | PWD Approval | Rebuild/PRA/AE |  | As Required | [6 empty] | Rebuild/AE/PPR
25 |  |  | CITY | Percent for Art Approval | Rebuild/PRA/AE |  | As Required | [6 empty] | Rebuild/AE/PPR
26 |  |  | AE | Zoning permit | Rebuild/PRA/AE |  | As Required | [6 empty] | Rebuild/AE/PPR
27 |  |  | AE/GC | Building Permit | Rebuild/PRA/AE |  | Pre Construction | [6 empty] | Rebuild/AE/PPR
28 |  |  | PRA/GC | Street /Sidewalk Closure Permit | Rebuild/PRA/AE |  | As Required | [6 empty] | Rebuild/AE/PPR
29 |  |  | GC | Dust Mitigation Permit | Rebuild/PRA/AE |  | As Required | [6 empty] | Rebuild/AE/PPR
30 |  |  | GC | PPR Site Activity Permit | Rebuild/PRA/AE |  | Pre Construction | [6 empty] | Rebuild/AE/PPR
31 |  |  | PRA | Notice to Proceed | Rebuild/PRA/AE |  | For Record | [6 empty] | Rebuild/AE/PPR
32 |  |  | PRA | Construction Kick Off Meeting Minutes | Rebuild/PRA/AE |  | For Record | [6 empty] | Rebuild/AE/PPR
33 |  |  | GC | Project Schedule Update | Rebuild/PRA/AE |  | Monthly | [6 empty] | Rebuild/AE/PPR
34 |  |  | GC | 2 Week Look Ahead | Rebuild/PRA/AE |  | Bi Weekly | [6 empty] | Rebuild/AE/PPR
35 |  |  | GC | Payment Request (Rebuild format) | Rebuild/PRA/AE |  | Monthly | [6 empty] | Rebuild/AE/PPR
36 |  |  | PRA/GC | Project Specific Submittal log - Monthly Update | Rebuild/PRA/AE |  | Monthly | [6 empty] | Rebuild/AE/PPR
37 |  |  | GC | Change Order Request Form- KIRA | Rebuild/PRA/AE |  | As Required | [6 empty] | Rebuild/AE/PPR
38 |  |  | GC | Change Order Request Log | Rebuild/PRA/AE |  | Monthly | [6 empty] | Rebuild/AE/PPR
39 |  |  | GC | Request for Information Form | Rebuild/PRA/AE |  | As Required | [6 empty] | Rebuild/AE/PPR
40 |  |  | GC | Request for Information Log | Rebuild/PRA/AE |  | As Required | [6 empty] | Rebuild/AE/PPR
41 |  |  | Rebuild | EOP Review at 25% Project Completion | Rebuild/PRA/AE | [8 empty] | Rebuild/AE/PPR
42 |  |  | PRA | Construction Kick Off Meeting Minutes | Rebuild/PRA/AE |  | For Record | [6 empty] | Rebuild/AE/PPR
43 |  |  | PRA | Project Meeting Minutes- Bi-weekly | Rebuild/PRA/AE |  | Bi Weekly | [6 empty] | Rebuild/AE/PPR
44 |  |  | AE | AE Project Field Reports | Rebuild/PRA/AE |  | Bi Weekly | [6 empty] | Rebuild/AE/PPR
45 |  |  | Rebuild/AE | Notice of Correction | Rebuild/PRA/AE |  | As Required | [6 empty] | Rebuild/AE/PPR
46 |  |  | GC | Daily Report | Rebuild/PRA/AE |  | Daily | [6 empty] | Rebuild/AE/PPR
47 |  |  | GC | Report of Injury | Rebuild/PRA/AE |  | As Required | [6 empty] | Rebuild/AE/PPR
48 |  |  | GC | Maintain Special inspections Log | Rebuild/PRA/AE |  | As Required | [6 empty] | Rebuild/AE/PPR
49 |  |  | GC | Environmental Remediation Plan & Program | Rebuild/PRA/AE | N/A | As Required | [6 empty] | Rebuild/AE/PPR
50 |  |  | GC | Environmental Remediation Waste Disposal Certificates | Rebuild/PRA/AE | N/A | As Required | [6 empty] | Rebuild/AE/PPR
51 |  |  | GC | LEED certifications, (KIRA) | Rebuild/PRA/AE | N/A | As Required | [6 empty] | Rebuild/AE/PPR
52 |  |  | GC | Commisioning, as required | Rebuild/PRA/AE | N/A | As Required | [6 empty] | Rebuild/AE/PPR
53 |  |  | GC | L& I inspection Reports | Rebuild/PRA/AE |  | As Required | [6 empty] | Rebuild/AE/PPR
54 |  |  | PRA/GC | Project Specific Submittal log - Monthly Update | Rebuild/PRA/AE |  | Monthly | [6 empty] | Rebuild/AE/PPR
55 |  |  | PRA/GC | Notice of Substantial Completion | Rebuild/PRA/AE |  | Closeout | [6 empty] | Rebuild/AE/PPR
56 |  |  | GC | Punchlist Closeout | Rebuild/PRA/AE |  | Closeout | [6 empty] | Rebuild/AE/PPR
57 |  |  | GC | As built Documents | Rebuild/PRA/AE |  | Closeout | [6 empty] | Rebuild/AE/PPR
58 |  |  | GC | O & M Manuals | Rebuild/PRA/AE |  | Closeout | [6 empty] | Rebuild/AE/PPR
59 |  |  | GC | O & M Training | Rebuild/PRA/AE |  | Closeout | [6 empty] | Rebuild/AE/PPR
60 |  |  | GC | Temporary Certiciate of Occupancy- Certificate of Occupancy | Rebuild/PRA/AE | N/A | As Required | [6 empty] | Rebuild/AE/PPR
61 |  |  | PRA/GC | Project Closeout Audit- NICOLE | Rebuild/PRA/AE |  | Closeout | [6 empty] | Rebuild/AE/PPR
62 |  |  | PRA |  | Rebuild/PRA/AE | [8 empty] | Rebuild/AE/PPR
63 |  |  | PRA |  | Rebuild/PRA/AE | [8 empty] | Rebuild/AE/PPR
64 |  |  | PRA |  | Rebuild/PRA/AE | [8 empty] | Rebuild/AE/PPR
65 |  |  | PRA |  | Rebuild/PRA/AE | [8 empty] | Rebuild/AE/PPR
66 |  |  | PRA |  | Rebuild/PRA/AE | [8 empty] | Rebuild/AE/PPR
(Spec section)-01 | Division 2 |  | GC | Product Data per specs.. | Rebuild/PRA/AE | Enter | As Required | [6 empty] | AE/LA/PE
|  |  | GC | Product Data per specs.. | Rebuild/PRA/AE | Estimated | [7 empty] | AE/LA/PE
|  |  | GC | Product Data per specs | Rebuild/PRA/AE | Dates | [7 empty] | AE/LA/PE
|  |  | GC | Product Data per specs | Rebuild/PRA/AE | This | [7 empty] | AE/LA/PE
|  |  | GC | Product Data per specs | Rebuild/PRA/AE | Column | [7 empty] | AE/LA/PE
|  |  | GC | Product Data per specs | Rebuild/PRA/AE | ….. | [7 empty] | AE/LA/PE
|  |  | GC | Product Data per specs | Rebuild/PRA/AE | … | [7 empty] | AE/LA/PE
|  |  | GC | Product Data per specs | Rebuild/PRA/AE | … | [7 empty] | AE/LA/PE
|  |  | GC | Product Data per specs | Rebuild/PRA/AE | [8 empty] | AE/LA/PE
|  |  | GC | Product Data per specs | Rebuild/PRA/AE | [8 empty] | AE/LA/PE
|  |  | GC | Samples per specs | Rebuild/PRA/AE | [8 empty] | AE/LA/PE
|  |  | GC | Shop Drawings per specs | Rebuild/PRA/AE | [8 empty] | AE/LA/PE
|  |  | GC | Mock ups per specs | Rebuild/PRA/AE | [8 empty] | AE/LA/PE
|  |  | Submitted |  | SD | Shop Drawing
|  |  | Reviewed |  | S | Sample
Late
Returned
Resubmit
Not used